## To-Do List
Progress Report
| Phase 0 - Requirements Analysis, Planning and Design |  | 2% | In Progress | Due date: March 14, 2018
| TASK | Assigned | PRIORITY | STATUS | START DATE | DUE DATE | % COMPLETE | Column1 | NOTES
1 | Review and understand the requirements | All Team | Normal | Complete | 2018-04-16 | 2018-02-21 | 100%
2 | Submit High Level Architecture | Rola | Normal | Complete | 2018-02-21 |  | 100%
3 | Submit Progress report | Rola | Normal | Complete | 2018-02-21 |  | 100%
4 | Submit Problem Log - submit a template | Rola | Normal | Complete | 2018-02-21 |  | 100%
0
| Phase 1 - Installation Planning, Begin Installlation |  | 2.5% | In Progress | Due date: March 21, 2018
| TASK | Assigned | PRIORITY | STATUS | START DATE | DUE DATE | % COMPLETE | Column1 | NOTES
5 | Submit Final Architecture Diagram | Rola | Normal | Complete |  |  | 100%
6 | Submit High Level Installation and Configuration Plan with target completion dates and dependencies. | Hui | Normal | Complete |  |  | 100%
7 | Submit Task List identifying team and individual deliverable with target completion date and dependencies. | Carlos | Normal | Complete |  |  | 100%
8 | Submit Problem Log - on-going | Mostapha | Normal | Complete |  |  | 100% | Column1
9 | Submit Test Plan | Ahmad | Normal | Complete |  |  | 100%
10 | Build, configure and test a core system (build minimalist system) | All Team | Normal | Complete |  |  | 100%
12 | Submit evidence of working system | All Team | Normal | Complete |  |  | 100%
| Phase 2 - Final Implementation and Testing |  | 2.5% | Not Started | Due date: April 8, 2018
| TASK | Assigned | PRIORITY | STATUS | START DATE | DUE DATE | % COMPLETE | Column1 | NOTES
13 | Complete system installation and configuration including third party component integration | All Team | Normal | In Progress | 2018-03-20 | 2018-04-08 | 100%
13.1 | Install all packages | Carlos | Normal | Complete | 2018-03-20 | 2018-04-08 | 100%
13.2 | Implement basic security. | Rola | Normal | Complete | 2018-03-20 | 2018-04-08 | 100%
14 | Execute test plan | Ahmad | Normal | In Progress | 2018-03-20 | 2018-04-08 | 100%
15 | Submit Progress Report - on-going | Mostapha | Normal | Complete | 2018-03-20 | 2018-04-08 | 100%
16 | Submit Problem Log - on-going | Hui | Normal | Complete | 2018-03-20 | 2018-04-08 | 100% | Column1
17 | Submit evidence of working system | Rola | Normal | In Progress | 2018-03-20 | 2018-04-08 | 50%
| Phase 3 - Final Delivery & Project Demonstration |  | 8% | Not Started | Due date: April 19, 2018
| TASK | Assigned | PRIORITY | STATUS | START DATE | DUE DATE | % COMPLETE | Column1 | NOTES
18 | Implement final requirements | Rola | Normal | In Progress |  |  | 100%
18.1 | Content security, etc. | Hui | Normal | In Progress |  |  | 25%
19 | Submit Final Documentation Package | Rola | Normal | In Progress |  |  | 100%
20 | Submit Problem Log Report | Hui | Normal | Not Started |  |  | 100%
21 | Submit Test plan and results | Ahmad | Normal | Not Started |  |  | 100% | Column1
22 | Dry run your demo | All Team | Normal | Not Started |  |  | 100%
23 | Demonstrate a working system (refer to the project demonstration document for details). | All Team | Normal | In Progress |  |  | 100%
Demo
Each member will be required to demonstrate their mastery and full understanding of the final product.